## Instructions
We will use Excel
· First tab is your Project Plan Make sure you state the Project Name (name of the technology solution)
· Second tab is Resources which is list of your team members and what skills they bring to the project.
Project Plan
Tasks - can add new tasks to provide more detail (remember to use a verb for example: Create Dashboard Wireframe, Create virtual server in AWS)
% completed
Start Date - this is your planned date and eventually will change to your actual date.
Finish Date - this may change as you realize that some tasks take longer than others. You put in the comments that the date changed and why.
Resource Name is the person who responsible to get this done. It may be a team who is working on it, yet there is one person who is leading the effort.
Notes - comments which explain the updates to the plan (i.e.. problems, accomplishments)

## Capstone Project Plan
| Task Name | % Complete | Start Date | Finish Date | Resource Name | Notes
Phase | Project Name: Systems Monitoring Server
Start IFT 401
1 | SYSTEMS PLANNING
| Complete Project Concept document | 100% | 2023-08-21 | 2023-08-28 | Henry
| Complete Project Charter document | 0% | 2023-08-22 | 2023-09-01 | Jorge
2 | SYSTEMS ANALYSIS
| Create Process Map | 0% | 2023-09-01 | 2023-09-15 | Zemenu | Process map + requirements to be done concurrently. Going into JIRA as we build.
| Create Requrements | 0% | 2023-09-01 | 2023-09-15 | Henry | Process map + requirements to be done concurrently. Going into JIRA as we build.
| Place Requirements in JIRA | 0% | 2023-09-01 | 2023-09-15 | Martha, Jorge | Process map + requirements to be done concurrently. Going into JIRA as we build.
| Create Systems Analysis Document | 0% | 2023-09-15 | 2023-09-29 | Jorge
3 | SYSTEMS DESIGN
| Create User Interface (mockup) | 0% | 2023-09-29 | 2023-10-20 | Henry
| Create system screen mockup | 0% | 2023-09-29 | 2023-10-20 | Henry
| Create login screen mockup | 0% | 2023-09-29 | 2023-10-20 | Jorge
| Create issue screen mockup | 0% | 2023-09-29 | 2023-10-20 | Martha
| Create outward status page mockup | 0% | 2023-09-29 | 2023-10-20 | Zemenu
| Create alert screen mockup | 0% | 2023-09-29 | 2023-10-20 | H
| Create Infratructure Architecture (Network Topology) | 0% | 2023-09-29 | 2023-10-13 | Henry
| Create data tier architecture | 0% | 2023-09-29 | 2023-10-13 | Henry
| Create API architecture | 0% | 2023-09-29 | 2023-10-13 | Henry
| Create UI architecture | 0% | 2023-09-29 | 2023-10-13 | Jorge
| Create network/deployment architecture | 0% | 2023-09-29 | 2023-10-13 | Martha
| Create Information Architecture (ERD) | 0% | 2023-10-13 | 2023-10-31 | Zemenu
| Create Systems Design document | 0% | 2023-10-13 | 2023-10-31 | Martha
4 | Documentation
| Prepare Systems Analysis & Design document | 0% | 2023-10-31 | 2023-11-17 | Jorge
| Prepare Final Presentation | 0% | 2023-11-17 | 2023-12-01 | Zemenu
IFT 402 | SYSTEMS IMPLEMENTATION |  |  |  |  | Build & Test, Deploy/Installation/Changeover
Start IFT 402
| Post Systems Analysis & Design Document |  |  |  | Henry
Build 1: Establish Development Environment
| Establish dev VM with Docker |  |  |  | Jorge
| Build Dockerfile for dependencies |  |  |  | Martha
| Build AWS development server |  |  |  | Zemenu
| Create GitHub project |  |  |  | Henry
| Set up CI/CD |  |  |  | Henry
| Test and ensure all devs can build and deploy |  |  |  | Jorge
Build 2: Build/Test User Interface
| Establish template with create-react-app |  |  |  | Jorge | Includes unit tests in Jest
| Import patternfly UI framework |  |  |  | Martha | Includes unit tests in Jest
| Build login screen |  |  |  | Henry | Includes unit tests in Jest
| Build system management screen |  |  |  | Zemenu | Includes unit tests in Jest
| Build system details dialog |  |  |  | Zemenu | Includes unit tests in Jest
| Build issue screen |  |  |  | Martha | Includes unit tests in Jest
| Build issue details dialog |  |  |  | Jorge | Includes unit tests in Jest
| Build outward status page |  |  |  | Martha | Includes unit tests in Jest
| Build alerting screen |  |  |  | Henry | Includes unit tests in Jest
| Build alert setup dialog |  |  |  | Jorge | Includes unit tests in Jest
| Test routing and full app flow |  |  |  | Zemenu | Includes automated E2E tests
Build 3: Build /Test Application (Business Logic)
| Build base API Layer |  |  |  | Jorge | Including JWT authN/authZ
| Build AuthN API |  |  |  | Martha | Includes unit tests
| Build AuthZ API |  |  |  | Henry | Includes unit tests
| Build system API |  |  |  | Zemenu | Includes unit tests
| Build issues API |  |  |  | Zemenu | Includes unit tests
| Build alerting API |  |  |  | Martha | Includes unit tests
| Build status API |  |  |  | Jorge | Includes unit tests
| Integrate with UI code |  |  |  | Martha
| Generate Postman library for all APIs |  |  |  | Henry
| Perform end-to-end test of UI + API |  |  |  | Jorge | Includes automated E2E tests
Build 4: Build/Test Database
| Build base data access library (Mongoose) |  |  |  | Zemenu | Includes unit tests
| Build user schema and DAO |  |  |  | Martha | Includes unit tests
| Build system schema and DAO |  |  |  | Jorge | Includes unit tests
| Build issue schema and DAO |  |  |  | Martha | Includes unit tests
| Build alerting schema and DAO |  |  |  | Henry | Includes unit tests
| Build status schema and DAO |  |  |  | Martha | Includes unit tests
| Integrate with API code |  |  |  | Henry | Includes automated E2E tests
| Perform comprehensive full system tests |  |  |  | Zemenu
Establish Production Environment
| Deploy system to production |  |  |  | Henry
Documentation
| Build 1 Deck |  |  |  | Jorge
| Build 1 Video |  |  |  | Jorge
| Build 2 Deck |  |  |  | Zemenu
| Build 2 Video |  |  |  | Zemenu
| Build 3 Deck |  |  |  | Martha
| Build3 Video |  |  |  | Martha
| Final Build Deck |  |  |  | Henry
| Final Build Video |  |  |  | Henry
IFT 402 | SYSTEMS SUPPORT/MAINTENANCE |  |  |  |  | User Training, Production Control documents,
| Create Showcase Presentation |  |  |  | Jorge

## Resources
Project Name: | Resources which is list of your team members and what skills they bring to the project.
Team Member | Skills | Notes
Henry Zektser | Architecture, Programming, Systems Design, Networking
Zemenu Guanche | Networking, Troubleshooting, Documentation,System Security
Jorge Castro | System security, Network, Analysis
Martha Agbugui | Troubleshooting, Monitoring